## Slide 1: Paper tasks and timeline

## Slide 2: Tasks to do
PCAR and PCTAR models
  Verify implementation
  Run penalty sensitivity analysis
  Identify best penalty value
Identify low price, high price and medium price scenarios – 10 each
  30 points for histogram of runtimes
Run all models on new cases
Train 2 (or 4) new neural networks for neuron sensitivity
Run neuron sensitivity analysis
ReLu DNN fundamental analysis
  Identify what to add here
  Implement
Write paper

## Slide 3: Timeline
16/09/24 – 22/09/24
Identify price scenarios
Run PWL, uNN and cNN models with the price scenarios
Verify PCAR and PCTAR models
Penalty sensitivity analysis
23/09/24 – 30/09/24
Run PCAR and PCTAR models with new price scenarios
Train 2 new set of Neural networks for neuron sensitivity analysis
ReLu DNN fundamental analysis – definition and implementation
Start writing the paper

## Slide 4: Timeline
01/10/24 – 15/10/24
Finish the first draft of the paper
Notes for Ali for this task:
I need to do this to break my habit of slow writing
To push myself I will add you to the blank document so you can track daily status
I will need you to push me to achieve this!!!!